## PLENARY LOA_7May2025
CGMS-53-CGMS-WP-25
Status of CGMS-52 Plenary actions (7 May 2025)
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status
CGMS members | 2 | A52.01 | WIGOS Vision 2040 update: CGMS members invited to nominate a CGMS representative to the WMO Task Team for the updating of the WIGOS Vision 2040. CGMS members are requested to send nominations to CGMSSEC@eumetsat.int by end June. | 07 May 2025 WMO to provide a status and way forward report to plenary CGMS-53-WMO-WP-08, and CGMSSEC will present the plan for a coordinated space agency response to the WIGOS Vision update CGMS-53-CGMS-WP-08 26 Mar 2025 WMO provided a status report to CGMS-53 WGIII, CGMS-53-WMO-WP-05; CGMSSEC proposal CGMS-53-CGMS-WP-13 26 Nov 2024 WMO plans to provide a status report to WGIII IS#3 (by the Chair Sid Boukabara/NASA) CGMS-53-WMO-WP-08 | 30 Jun 2024 | CLOSED
06 Nov 2024 The CGMS Secretariat is currently represented by Sean.burns@eumetsat.int
27 Jun 2024 NASA nominates Mike Seablom, Associate Director of the Earth System Technology Office in the NASA Earth Science Division (michael.s.seablom@nasa.gov)
CGMS members | 5 | A52.02 | WG reports to plenary: Members to provide nominations for the WGI co-rapporteur, WGII co-chair position, and WGIV co-chair in particular, as well as other CGMS associated positions as per CGMS-52-CGMS-WP-11p, 6 June 2024, v4 | 27 Mar 2025 CGMS-53 working groups: WGI co-chair: Sean Burns, EUMETSAT (acting) WGII co-chair: Takuya Sakashita, JMA, recommended to plenary for confirmation. WGIV co-chair: Natalia Donoho, WMO, recommended as co-chair to plenary. SWCG co-chair: James Spann, NOAA, recommended as co-chair to plenary. VLab: CGMS space agency representative: XIAN Di, CMA, nominated to replace Bernie Connell, for plenary endorsement. | 30 Jun 2024 | ONGOING
26 Feb 2025 The SWCG co-chair Elsayed Talaat, NOAA, has stepped down as co-chair, with James Spann, NOAA, acts as interim. Nominations/elections to be held at the CGMS-53 SWCG. 12 Feb 2025 WGIV IS: WMO has nominated Natalia Donoho as co-chair of WGIV. If confirmed by plenary 53, there will be a need for a new WGIV co-rapporteur (20 Nov 2024 The WGI co-chair, Dohyeong Kim, KMA, has informed the CGMS Secretariat he will need to step down as co-chair). Sean Burns, EUMETSAT, will support as acting WGI co-chair. 01 Oct 2024 WGII co-chair: Takuya SAKASHITA, JMA, has been nominated as the new co-chair for WGII and will replace Dr JV Thomas, ISRO, over the coming months.
CGMS members | 4, 8 | A52.03 | WGClimate/G3W: | 03 Jul 2024 Action superseded by events. Simon Elliott, EUMETSAT, nominated as the focal point of contact/lead on WGClimate/GHG TT/G3W/and CGMS operational matters. CGMS-52 plenary endorsed the nomination. | 30 Jun 2024 | CLOSED
CGMS members to nominate two representatives to take the proposals in https://www.cgms-info.org/Agendas/PPT/CGMS-52-EUMETSAT-WP-13p forward.
Following feedback, CGMSSEC will address next steps with WGClimate. (+ need for dedicated intersessional meeting between the CGMS WGs and WGClimate).
CGMS members | 8 | A52.04 | AI-ML next steps: proposed use cases for CGMS | 07 May 2025 Joe Turk, NASA, IPWG rapporteur will make a presentation to plenary (CGMS-53-IPWG-WP-04). | 2024-06-30 | ONGOING
|  |  | CGMS members to provide comments and feedback on the proposals in https://www.cgms-info.org/Agendas/PPT/CGMS-52-WGII-WP-04 | 27 Mar 2025 The IPWG made a presentation to CGMS-53 WGII (CGMS-53-IPWG-WP-02) "AI and satellite integration - proposals for CGMS including further analysis from the IPWG, examining the impact of direct satellite data usage in machine learning training" https://www.cgms-info.org/Agendas/GetWpFile.ashx?wid=347d1b7e-4ac2-40d9-9bc0-19cd2e5ee1de&aid=d343a39c-fbdd-4638-97c4-158894dcb97f
|  |  | CGMS members to nominate two focal points of contact as leading entity to pursue this activity. | The SWCG has been tasked to identify an AI/ML use case presentation for plenary.
|  |  | Following feedback, CGMSSEC will address next steps with WGI, WGII and WGIV leading entities. | 25 Feb 2025 Important for members to come forward with nominations to drive this initiative forward.
CGMS-52 Plenary Recommendations
Leading entities | AGN item | Rec # | Description | Recommendation feedback/closing document
CGMS members | WMO MATTERS FOR COORDINATION WITH CGMS SPACE AGENCIES | R51.01 | Plenary recommended that CGMS members actively support and respond to the WMO strategic initiatives and resolutions, such as EW4ALL, G3W, and Unified Data Policy implementation. | 27 Mar 2025 CGMS-53 WGIII, recommendation remains valid. WMO recalls CM-16 on 3-4 March 2026 and the participation of CGMS space agency heads.
|  |  | (Original recommendation: Plenary recommended that CGMS members actively support and respond to the WMO strategic initiatives and resolutions, such as EW4ALL, G3W, and Unified Data Policy implementation; and asks CGMS space agency members to participate in the upcoming Core Satellite Data Workshop (4-7 December 2023) and WMO Consultative Meetings on High-level Policy on Satellite Matters (Feb 2024).) | 04 Jun 2024 https://www.cgms-info.org/Agendas/PPT/CGMS-52-WMO-WP-03p, https://www.cgms-info.org/Agendas/PPT/CGMS-52-WMO-WP-02p Recommendation carried over to CGMS-52 actions and recommendations 09 Apr 2024 Most CGMS members participated in the NWP core satellite data workshop, and CM-15 and provided their inputs to WMO.
CGMS members | WMO MATTERS FOR COORDINATION WITH CGMS SPACE AGENCIES | R51.02 | (Action to be monitored by WGIV) | 27 Mar 2025 CGMS-53 WGIII. This recommendation remains valid, and also valid for the WMO space programme trust fund.
| (WGIV/6) | (WGIV/(P)A50.01) | CGMS members are invited to contact WMO to provide contributions to the WMO VLab Trust Fund to ensure the continuation of technical support to the VLab through the VLab Technical Support Officer as well as to the implementation of VLab projects. | 04 Jun 2024 https://www.cgms-info.org/Agendas/PPT/CGMS-52-VLab-WP-01p, https://www.cgms-info.org/Agendas/PPT/CGMS-52-GUEST-WP-03 Recommendation carried over to CGMS-52 actions and recommendations
23 Apr 2024 Addressed at CGMS-52 WGIV meeting. WMO expected to address this in detail at CGMS-52 plenary,
2023 11 July: Noted as a recommendation by the CGMS Secretariat
2023 28 June: Plenary endorsed the recommendation in the report by the VLab to plenary. The "action" still remains valid.
2023 19 June: CGMS members are kindly requested to contribute to the VLab to secure the continuity of this valuable activity.
2023 2 June: Topic to be raised in the report of the WGIV CGMS-51-WGIV-WP-01 EXT and VLab CGMS-51-VLab-WP-02 EXT to plenary.