## CGMS-52
CGMS-52 LOA
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status
CGMS members | 2 | A52.01 | WIGOS Vision 2040 update: CGMS members invited to nominate a CGMS representative to the WMO Task Team for the updating of the WIGOS Vision 2040. CGMS members are requested to send nominations to CGMSSEC@eumetsat.int by end June. | 07 May 2025 WMO to provide a status and way forward report to plenary CGMS-53-WMO-WP-08, and CGMSSEC will present the plan for a coordinated space agency response to the WIGOS Vision update 06 Nov 2024 The CGMS Secretariat is currently represented by Sean.burns@eumetsat.int 27 Jun 2024 NASA nominates Mike Seablom, Associate Director of the Earth System Technology Office in the NASA Earth Science Division (michael.s.seablom@nasa.gov) | 30 Jun 2024 | CLOSED
CGMS members | 5 | A52.02 | WG reports to plenary: Members to provide nominations for the WGI co-rapporteur, WGII co-chair position, and WGIV co-chair in particular, as well as other open positions as per https://www.cgms-info.org/Agendas/WP/CGMS-52-CGMS-WP-11p | 3-5 June 2025: Closure proposed. Status/updates provided and endorsed by CGMS-53 plenary. Non-represented CGMS members are nevertheless invited to consider supporting the leading entities of the five working groups. | 30 Jun 2024 | CLOSED
27 March 2025: CGMS-53 WGs status: WGI co-chair: Sean Burns, EUMETSAT (acting)
WGII co-chair: Takuya Sakashita, JMA, recommended to plenary for confirmation.
WGIV co-chair: Natalia Donoho, WMO, recommended as co-chair to plenary.
SWCG co-chair: James Spann, NOAA, recommended as co-chair to plenary.
VLab: CGMS space agency representative: XIAN Di, CMA, nominated to replace Bernie Connell, for plenary endorsement.
26 Feb 2025 The SWCG co-chair Elsayed Talaat, NOAA, has stepped down as co-chair, with James Spann, NOAA, acts as interim. Nominations/elections to be held at the CGMS-53 SWCG.
12 Feb 2025 WGIV IS: WMO has nominated Natalia Donoho as co-chair of WGIV. If confirmed by plenary 53, there will be a need for a new WGIV co-rapporteur
(20 Nov 2024 The WGI co-chair, Dohyeong Kim, KMA, has informed the CGMS Secretariat he will need to step down as co-chair). Sean Burns, EUMETSAT, will support as acting WGI co-chair.
01 Oct 2024 WGII co-chair: Takuya SAKASHITA, JMA, has been nominated as the new co-chair for WGII and will replace Dr JV Thomas, ISRO, over the coming months.
Nominations for WGI co-rapporteur and WGIV co-chairs are still outstanding.
CGMS members | 4, 8 | A52.03 | WGClimate/G3W: | 03 Jul 2024 Action superseded by events. Simon Elliott, EUMETSAT, nominated as the focal point of contact/lead on WGClimate/GHG TT/G3W/and CGMS operational matters. CGMS-52 plenary endorsed the nomination. | 30 Jun 2024 | CLOSED
CGMS members to nominate two representatives to take the proposals in https://www.cgms-info.org/Agendas/PPT/CGMS-52-EUMETSAT-WP-13p forward.
Following feedback, CGMSSEC will address next steps with WGClimate.
(+ need for dedicated intersessional meeting between the CGMS WGs and WGClimate).
CGMS members | 8 | A52.04 | AI-ML next steps: proposed use cases for CGMS CGMS members to provide comments and feedback on the proposals in https://www.cgms-info.org/Agendas/PPT/CGMS-52-WGII-WP-04 CGMS members to nominate two focal points of contact as leading entity to pursue this activity. Following feedback, CGMSSEC will address next steps with WGI, WGII and WGIV leading entities. | 5 June 2025: CLOSURE PROPOSED following presentations in CGMS-53 plenary item 6 on AI use cases and item 9. | 2024-06-30 | CLOSED
21 May 2025 T Nagatsuma, NICT, SWCG co-chair, will make a presentation to plenary on AI and space weather (CGMS-53-SWCG-WP-16 07 May 2025 Joe Turk, NASA, IPWG rapporteur will make a presentation to plenary including several agency cases (CGMS-53-WGII-WP-08).
27 Mar 2025 The IPWG made a presentation to CGMS-53 WGII (CGMS-53-IPWG-WP-02) "AI and satellite integration - proposals for CGMS including further analysis from the IPWG, examining the impact of direct satellite data usage in machine learning training" https://www.cgms-info.org/Agendas/GetWpFile.ashx?wid=347d1b7e-4ac2-40d9-9bc0-19cd2e5ee1de&aid=d343a39c-fbdd-4638-97c4-158894dcb97f
The SWCG has been tasked to identify an AI/ML use case presentation for plenary.
Joe Turk, NASA, IPWG rapporteur to CGMS, nominated as champion.
25 Feb 2025 Important for members to come forward with nominations to drive this initiative forward.
Leading entities | AGN item | Rec # | Description | Recommendation feedback/closing document
CGMS members | WMO MATTERS FOR COORDINATION WITH CGMS SPACE AGENCIES | R51.01 | Plenary recommended that CGMS members actively support and respond to the WMO strategic initiatives and resolutions, such as EW4ALL, G3W, and Unified Data Policy implementation. | 3-5 June 2025 Recalled on the occasion of the CGMS-53 plenary. 27 Mar 2025 CGMS-53 WGIII, recommendation remains valid. WMO recalls CM-16 on 3-4 March 2026 and the participation of CGMS space agency heads.
04 Jun 2024 https://www.cgms-info.org/Agendas/PPT/CGMS-52-WMO-WP-03p, https://www.cgms-info.org/Agendas/PPT/CGMS-52-WMO-WP-02p Recommendation carried over to CGMS-52 actions and recommendations
|  |  | (Original recommendation: Plenary recommended that CGMS members actively support and respond to the WMO strategic initiatives and resolutions, such as EW4ALL, G3W, and Unified Data Policy implementation; and asks CGMS space agency members to participate in the upcoming Core Satellite Data Workshop (4-7 December 2023) and WMO Consultative Meetings on High-level Policy on Satellite Matters (Feb 2024).) | 09 Apr 2024 Most CGMS members participated in the NWP core satellite data workshop, and CM-15 and provided their inputs to WMO.
CGMS members | WMO MATTERS FOR COORDINATION WITH CGMS SPACE AGENCIES | R51.02 | (Action to be monitored by WGIV) | 3-5 June 2025 Recalled on the occasion of the CGMS-53 plenary. 27 Mar 2025 CGMS-53 WGIII. This recommendation remains valid, and also valid for the WMO space programme trust fund.
| (WGIV/6) | (WGIV/(P)A50.01) | CGMS members are invited to contact WMO to provide contributions to the WMO VLab Trust Fund to ensure the continuation of technical support to the VLab through the VLab Technical Support Officer as well as to the implementation of VLab projects. | 04 Jun 2024 https://www.cgms-info.org/Agendas/PPT/CGMS-52-VLab-WP-01p, https://www.cgms-info.org/Agendas/PPT/CGMS-52-GUEST-WP-03 Recommendation carried over to CGMS-52 actions and recommendations
23 Apr 2024 Addressed at CGMS-52 WGIV meeting. WMO expected to address this in detail at CGMS-52 plenary,
2023 11 July: Noted as a recommendation by the CGMS Secretariat
2023 28 June: Plenary endorsed the recommendation in the report by the VLab to plenary. The "action" still remains valid.
2023 19 June: CGMS members are kindly requested to contribute to the VLab to secure the continuity of this valuable activity.
2023 2 June: Topic to be raised in the report of the WGIV CGMS-51-WGIV-WP-01 EXT and VLab CGMS-51-VLab-WP-02 EXT to plenary.

## CGMS-53
GMS-53 Plenary Actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
WMO, GHG TT | 4 | 53 | WMO and GHG Task Team work on baseline requirements for operational GHG monitoring (considering requirements for revisiting time (mapping capabilities), product timeliness, and product availability and completeness) that ensures a common understanding of the requirements and can function as a guideline for the utilisation of current and the establishment of future missions including from the commercial sector. |  | CGMS-54 | OPEN
WMO, GHG TT | 4 | 53. | WMO and the GHG Task Team capture the requirements of IMEO and other interested applications for methane observations from geostationary orbit. These are necessary to enable an operational implementation at CGMS agencies. |  | CGMS-54 | OPEN
CGMS members | 4 | 53. | CGMS members to provide feedback on the draft common practice document for remote sensing-based estimates of facility-scale emissions to Paul Green (paul.green@npl.co.uk) & John Worden (john.r.worden@jpl.nasa.gov) copy to CGMSSEC@eumetsat.int |  | 2025-06-30 | OPEN
https://www.cgms-info.org/Agendas/GetWpFile.ashx?wid=46ed374b-19bd-4ea8-92d7-26051665f580&aid=16bce6f8-3abf-44a7-88d2-38abff9bd878
https://www.cgms-info.org/Agendas/GetWpFile.ashx?wid=46ed374b-19bd-4ea8-92d7-26051665f580&aid=bcbf0183-4b5d-4046-be17-e2aa087e84a1
CGMS members | 4 | 53 | Paul Green to submit the final version of the common practice document for remote sensing-based estimates of facility-scale emissions to CGMSSEC@eumetsat.int for further circulation to and confirmation by CGMS members. |  | 1 Oct 2025, 30 Nov 2025 | OPEN
CGMS members | 4 | 53 | The Chairperson of the 2 June side meeting proposed to provide the outline of the updated GST strategy to the CGMS Secretariat by end June, and CGMS members will be requested to provide feedback to the CGMSSEC by September 2025 confirming if CGMS in principle should join the strategy by formally endorsing it at Plenary level by correspondence by end 2025 (on the understanding that CEOS SIT concurs to a joint document). |  | 30 June, 30 Sept, | OPEN
IESWG leading entity | 5 | 53 | On IESWG: IESWG to share with CGMSSEC (for redistribution to CGMS members) the outcome of its June 2025 meeting, incl. updated ToRs, and for further reporting to CGMS-54 |  | 15 Aug, (CGMS-54) | OPEN
CGMSSEC, CGMS members | 9 | 53 | Proposed activity: CGMS Secretariat to survey CGMS contributing agencies; WGII and WGIV and proposing initial standards to be presented at CGMS-54 (To facilitate the use of AI/ML by CGMS contributing agencies and meteorological data users, CGMS shall identify standards for using and converting meteorological EO data into a suitable form for Machine Learning applications. The key elements to be addressed are: + Data standards and formats, such as for example the Zarr usage best + practices Most relevant data transformation/representation per measurement type, i.e., remapping, standard vertical grids, etc. + Adoption of standard metadata per measurement type, preferably using CF metadata conventions, i.e., source of the information, AI fused or original data, error characterization of original and fused data.) |  | CGMS-54 | OPEN
CGMS members | 7 | 53 | CGMS members to review the revised HLPP 2025-2029 (https://www.cgms-info.org/Agendas/WP/CGMS-53-CGMS-WP-27) and provide feedback if/as necessary to cgmssec@eumetsat.int |  | 2025-06-23 | OPEN
RECOMMENDATIONS
CGMS space agency members | 5 | 53 | On ITWG : Instrument disaggregation: As part of future architecture analysis, due attention must be given to ensure that the disaggregation of instruments, does not degrade the time/space coincident measurements in different spectral ranges currently found in the backbone missions, as disaggregation could impede the effectiveness of various meteorological and environmental applications such as for example severe weather nowcasting or large scale aerosol/ash plume monitoring.