## New actions
CGMS-54 List of plenary actions
Action # | Actionee | AGN item | Description | Action feedback/closing document | Deadline | Status
54.01p | CGMSSEC, WMO | WMO | CGMSSEC and WMO to decide the dates for CM-17 in 2028 |  | End of 2026 | OPEN
54.02p | CGMS Agencies | WGIV | CGMS space agencies to consider contributing to the WMO VLab Trust Fund to support the continuation of VLab technical coordination activities and training delivery, including travel support for WMO Members with limited resources |  | CGMS-55 | OPEN
54.03p | CGMS Agencies | WGIV | CGMS space agencies to consider reviewing the draft revised VLab Strategy for Education and Training in Satellite Meteorology (2027–2030) and take note of the planned endorsement process prior to its submission to INFCOM-4 |  | INFCOM-4 (Oct/Nov 2026) | OPEN
54.04p | CGMS Operators | SWCG | CGMS satellite operators to suggest measures to enable satellite anomaly data supply |  | SWCG IS#1 (24 September 2026) | OPEN | converted to plenary action from SWCG report
54.05p | CGMS Members | AI/ML | Establish a list of experts from CGMS Members and CGMS Working Groups to form an AI Task Team, identifying the way forward for CGMS to address AI matters and prepare the future WMO/CGMS AI workshop |  | End of 2026 | OPEN | *
54.06p | CGMS Members | HLPP | CGMS members to provide final comments on the HLPP for a revised version covering the period 2026-2030 |  | 19 June | OPEN | *
CGMS-54 List of plenary actions to WGI
Action # | Actionee | AGN item | Description | Action feedback/closing document | Deadline | Status
54.01p_wgi | CGMSSEC, WMO | WGI | Work together to prepare a paper for INFCOM-4 addressing the proposed update of the Manual on the WIGOS |  | INFCOM-4 (Oct/Nov 2026) | OPEN
54.02p_wgi | CGMS Agencies | WGI | CGMS space agencies to provide experts to the work of the WMO Expert Team on Radio Frequency Coordination (ET-RFC) |  | 30 Sep 2026 | OPEN
54.01p_wgi | CGMS Operators | WGI | CGMS satellite operators to contribute operational expertise and inputs to WGI Space Environment Sustainability (SES) Task Group activities through expanded membership from further organisations |  | End of 2026 | OPEN
CGMS-54 List of plenary actions to WGII
Action # | Actionee | AGN item | Description | Action feedback/closing document | Deadline | Status
54.01p_wgii | WGII | WGII | Discuss the coordination for lightning imager validation methodologies and for extending the GEO-ring concept to lightning at the next intersessional meetings |  | End of 2026 | OPEN
54.02p_wgii | WGII | WGII | Encourage the NWP community to assess the quality and impact of different satellite products, such as derived 3D wind products from IR sounders, as soon as possible after the data come online. (Explore this through NWP agencies and via WMO operational and research groups) |  | CGMS-55 | OPEN
54.03p_wgii | WGII | WGII | Establish a new Operational fire detection Task Force to investigate fire channels intercalibration, fire products and harmonisation |  | End of 2026 | OPEN
CGMS-54 List of plenary actions to WGIII
Action # | Actionee | AGN item | Description | Action feedback/closing document | Deadline | Status
54.01p_wgiii | IROWG | WGIII | IROWG to assess the impact of the decline in COSMIC data availability, possibly distinguishing between the respective contributions of low- and medium- inclination orbit, and analysing the number of RO required to mitigate the risk |  | End of 2026 (9th WGIII RAWS: 24-26 Feb 2027) | OPEN
54.02p_wgiii | WGIII | WGIII | CGMS Risk Assessment 2027 (supported by the WMO Gap Analysis) to analyse the long-term continuity of the Earth Radiation Budget satellite measurements in response to the request from the World Climate Research Program (WCRP) and the Global Energy and Water Exchanges (GEWEX) |  | 9th WGIII RAWS: 24-26 Feb 2027 | OPEN
CGMS-54 List of plenary actions to WGIV
Action # | Actionee | AGN item | Description | Action feedback/closing document | Deadline | Status
54.01p_wgiv | WGIV Task Group on Data Access and Exchange | WGIV | WGIV to address Data Access from Web Platforms, looking for commonalities and the possible development of Good Practices. This activity is to be included in the work of the WGIV Task Group on Data Access and Exchange |  | End of 2026 | OPEN
CGMS-54 List of plenary actions to SWCG
Action # | Actionee | AGN item | Description | Action feedback/closing document | Deadline | Status
null